## Title
OFT Operations Excellence Strategy Plan V21™
Copyright © 2000 to 2020 AfCI LLC All Rights Reserved
OE21 Continuous Improvement Tool (OFT v.21)
Warning: This computer program is protected by copyright law in the United States and international treaties including the Berne Convention. Unauthorized reproduction or distribution of this program, or any portion of it, may result in severe civil and criminal penalties, and will be prosecuted to the maximum extent possible under the law. For each instance in which a United States Court finds that infringement was committed willfully, the court in its discretion may increase the award of statutory damages to a sum of not more than $150,000.

## SimplePlan
Project Title:
Project ID:
Project Manager:
Project Control:
Planned Start Date
Planned Finished Date
| Budget At Completion (Contract Target Cost) | 0
A | PROJECT DESCRIPTION | C | D | E | F | G | H | I | J | K
|  | Responsible for Task | Input Status Date | Input Percent Completed (EV) | Input Planned Start Date | Input Estimated Finish Date | Input Planned LABOR hours or "0" of Non-Labor (Material, other) | Input Labor Rate/Hours or Non-Labor Dollars ($) | Input Actual Costs from Accounting Records | BAC (Budget-At- Completion)
# | Task Descriptions | Responsible | Status Date | %Complete | Start Date | Finish Date | Lhrs or NL$ | Lrate or NL$ | Actual Costs | Labor + NonL $
1 | bar: C to J
2
3 | bar: C to J
4
5 | bar: C to J
6
7 | bar: C to J
8
9 | bar: C to J
10
11 | bar: C to J
12
13 | bar: C to J
14
15 | bar: C to J
16
17 | bar: C to J
18
19 | bar: C to J
20
21 | bar: C to J
22
23 | bar: C to J
24
25 | bar: C to J
26
27 | bar: C to J
28
29 | bar: C to J
30
31 | bar: C to J
32
33 | bar: C to J
34
35 | bar: C to J
36
37 | bar: C to J
38
39 | bar: C to J
40
41 | bar: C to J
42
43 | bar: C to J
44
45 | bar: C to J
46
47 | bar: C to J
48
49 | bar: C to J
50
51 | bar: C to J
52
53 | bar: C to J
54
55 | bar: C to J
56
57 | bar: C to J
58
59 | bar: C to J
60
61 | bar: C to J
62
63 | bar: C to J
64
65 | bar: C to J
66
67 | bar: C to J
68
69 | bar: C to J
70
71 | bar: C to J
72
73 | bar: C to J
74
75 | bar: C to J
76
77 | bar: C to J
78
79 | bar: C to J
80
81 | bar: C to J
82
83 | bar: C to J
84
85 | bar: C to J
86
87 | bar: C to J
88
89 | bar: C to J
90
91 | bar: C to J
92
93 | bar: C to J
94
95 | bar: C to J
96
97 | bar: C to J
98
99 | bar: C to J
100

## DetailedPlan
| Project Title: |  |  |  |  | ANALYSIS NOTES
| Project ID: |  |  |  | 1
| Project Manager: |  |  |  | 2
| Project Control: |  |  |  | 3
| Project Status Date: |  |  |  | 4
| Planned Finished Date |  |  |  | 5
New Forcasted Finished Date
| Budget At Completion (BAC) | 0 | PM Estimate: | 0
EV Cumulative to Date:
| AC Cumulative to Date: | 0
WS Cumulative to Date:
| Cost Variance (EV - AC) | 0 | CPI
| Schedule Variance (EV - WS) | 0 | SPI
A | PROJECT DESCRIPTION | C | D | E | F | G | H | I | J | K | L | M | N | O | P | Q | R | S
|  | Responsible for Task | Input Status Date | Input Percent Completed (EV) | Input Planned Start Date | Input Estimated Finish Date | Input Planned LABOR hours or "0" of Non-Labor (Material, other) | Input Labor Rate/Hours or Non-Labor Dollars ($) | Input Actual Costs from Accounting Records | BAC (Budget-At- Completion) | WS Work Scheduled | EV Earned Value | AC Actual Cost | SV = (EV-WS) | CV = (EV-AC) | WS Work Scheduled $ | EV Earned Value ($) | AC (cum.) Actual Cost
# | Task Descriptions | Responsible | Status Date | %Complete | Start Date | Finish Date | Lhrs or NL$ | Lrate or NL$ | Actual Costs | Labor + NonL $ | WS | EV | AC | SV | CV | WS Cum$ | EV Cum$ | AC Cum$ | STATUS | BAC | WS | EV | AC | SV | CV
1 | bar: 0 C to SPI J
2
3 | bar: 0 C to SPI J
4
5 | bar: 0 C to SPI J
6
7 | bar: 0 C to SPI J
8
9 | bar: 0 C to SPI J
10
11 | bar: 0 C to SPI J
12
13 | bar: 0 C to SPI J
14
15 | bar: 0 C to SPI J
16
17 | bar: 0 C to SPI J
18
19 | bar: 0 C to SPI J
20
21 | bar: 0 C to SPI J
22
23 | bar: 0 C to SPI J
24
25 | bar: 0 C to SPI J
26
27 | bar: 0 C to SPI J
28
29 | bar: 0 C to SPI J
30
31 | bar: 0 C to SPI J
32
33 | bar: 0 C to SPI J
34
35 | bar: 0 C to SPI J
36
37 | bar: 0 C to SPI J
38
39 | bar: 0 C to SPI J
40
41 | bar: 0 C to SPI J
42
43 | bar: 0 C to SPI J
44
45 | bar: 0 C to SPI J
46
47 | bar: 0 C to SPI J
48
49 | bar: 0 C to SPI J
50
51 | bar: 0 C to SPI J
52
53 | bar: 0 C to SPI J
54
55 | bar: 0 C to SPI J
56
57 | bar: 0 C to SPI J
58
59 | bar: 0 C to SPI J
60
61 | bar: 0 C to SPI J
62
63 | bar: 0 C to SPI J
64
65 | bar: 0 C to SPI J
66
67 | bar: 0 C to SPI J
68
69 | bar: 0 C to SPI J
70
71 | bar: 0 C to SPI J
72
73 | bar: 0 C to SPI J
74
75 | bar: 0 C to SPI J
76
77 | bar: 0 C to SPI J
78
79 | bar: 0 C to SPI J
80
81 | bar: 0 C to SPI J
82
83 | bar: 0 C to SPI J
84
85 | bar: 0 C to SPI J
86
87 | bar: 0 C to SPI J
88
89 | bar: 0 C to SPI J
90
91 | bar: 0 C to SPI J
92
93 | bar: 0 C to SPI J
94
95 | bar: 0 C to SPI J
96
97 | bar: 0 C to SPI J
98
99 | bar: 0 C to SPI J
100
0

## SimplePlan Example
| Project Title: | XYZ Power Facility
| Project ID: | A0902
| Project Manager: | John Wayne
| Project Control: | Annie Oakley
| Planned Start Date | 2018-01-05
| Planned Finished Date | 2018-05-01
| Budget At Completion (BAC) | 102510
A | PROJECT DESCRIPTION | C | D | E | F | G | H | I | J | K
| The XYZ Power Facility is a special building for local housing street lights and a new security alarm camera and storm warning siren system that meets Dept of Homeland Security Spec No. 4xx21alp12 | Responsible for Task | Input Status Date | Input Percent Completed (EV) | Input Planned Start Date | Input Estimated Finish Date | Input Planned LABOR hours or "0" of Non-Labor (Material, other) | Input Labor Rate/Hours or Non-Labor Dollars ($) | Input Actual Costs from Accounting Records | BAC (Budget-At- Completion)
# | Task Descriptions | Responsible | Status Date | %Complete | Start Date | Finish Date | Lhrs or NL$ | Lrate or NL$ | Actual Costs | Labor + NonL $
1 | Purchase Items for Power Facility construction | Purchasing |  |  | 2018-01-05 | 2018-01-10 | 0 | 25000 |  | 25000
2 | File and receive permits | Project Team A1 |  |  | 2018-01-10 | 2018-01-31 | 16 | 100 |  | 1600
3 | Prepare foundation | Supplier Alpha |  |  | 2018-02-01 | 2018-02-05 | 24 | 35 |  | 840
4 | Pour cement for foundation | Supplier Alpha |  |  | 2018-02-06 | 2018-03-01 | 16 | 35 |  | 560
5 | Construct building frame, including doors and windows | Supplier Bravo |  |  | 2018-02-08 | 2018-03-31 | 512 | 55 |  | 28160
6 | Construct building roof | Supplier Bravo |  |  | 2018-03-11 | 2018-04-02 | 144 | 55 |  | 7920
7 | Install electric wiring, lights and panels | Supplier Charlie |  |  | 2018-03-21 | 2018-05-05 | 56 | 75 |  | 4200
8 | Install water and plumbing | Supplier Delta |  |  | 2018-03-29 | 2018-06-15 | 256 | 65 |  | 16640
9 | Install Drywall | Supplier Bravo |  |  | 2018-04-16 | 2018-07-20 | 48 | 55 |  | 2640
10 | Install floor and ceilings | Supplier Bravo |  |  | 2018-04-21 | 2018-08-15 | 128 | 55 |  | 7040
11 | Paint and finish | Supplier Bravo |  |  | 2018-04-20 | 2018-09-10 | 42 | 55 |  | 2310
12 | Install fixtures for power equipment | Supplier Charlie |  |  | 2018-04-26 | 2018-10-02 | 64 | 75 |  | 4800
13 | Building ready for power equipment installation | Project Team A1 |  |  | 2018-05-01 | 2018-10-05 | 8 | 100 |  | 800
14
15 | bar: C to J
16
17 | bar: C to J
18
19 | bar: C to J
20
21 | bar: C to J
22
23 | bar: C to J
24
25 | bar: C to J
26
27 | bar: C to J
28
29 | bar: C to J
30
31 | bar: C to J
32
33 | bar: C to J
34
35 | bar: C to J
36
37 | bar: C to J
38
39 | bar: C to J
40
41 | bar: C to J
42
43 | bar: C to J
44
45 | bar: C to J
46
47 | bar: C to J
48
49 | bar: C to J
50
51 | bar: C to J
52
53 | bar: C to J
54
55 | bar: C to J
56
57 | bar: C to J
58
59 | bar: C to J
60
61 | bar: C to J
62
63 | bar: C to J
64
65 | bar: C to J
66
67 | bar: C to J
68
69 | bar: C to J
70
71 | bar: C to J
72
73 | bar: C to J
74
75 | bar: C to J
76
77 | bar: C to J
78
79 | bar: C to J
80
81 | bar: C to J
82
83 | bar: C to J
84
85 | bar: C to J
86
87 | bar: C to J
88
89 | bar: C to J
90
91 | bar: C to J
92
93 | bar: C to J
94
95 | bar: C to J
96
97 | bar: C to J
98
99 | bar: C to J
100

## DetailedPlan Example
| Project Title: | XYZ Power Facility |  |  |  | ANALYSIS NOTES
| Project ID: | A0902 |  |  | 1
| Project Manager: | John Wayne |  |  | 2
| Project Control: | Annie Oakley |  |  | 3
| Project Status Date: | 2018-03-31 |  |  | 4
| Planned Finished Date | 2018-10-05 |  |  | 5
| New Forcasted Finished Date | 2018-10-15
| Budget At Completion (BAC) | 102510 | PM Estimate: | 125000
| EV Cumulative to Date: | 13144
| AC Cumulative to Date: | 39300
| WS Cumulative to Date: | 27440
| Cost Variance (EV - AC) | -26156 | CPI | 0.33445
| Schedule Variance (EV - WS) | -14296 | SPI | 0.47901
A | PROJECT DESCRIPTION | C | D | E | F | G | H | I | J | K | L | M | N | O | P | Q | R | S
| The XYZ Power Facility is a special building for local housing street lights and a new security alarm camera and storm warning siren system that meets Dept of Homeland Security Spec No. 4xx21alp12 | Responsible for Task | Input Status Date | Input Percent Completed (EV) | Input Planned Start Date | Input Estimated Finish Date | Input Planned LABOR hours or "0" of Non-Labor (Material, other) | Input Labor Rate/Hours or Non-Labor Dollars ($) | Input Actual Costs from Accounting Records | BAC (Budget-At- Completion) | WS Work Scheduled | EV Earned Value | AC Actual Cost | SV = (EV-WS) | CV = (EV-AC) | WS Work Scheduled $ | EV Earned Value ($) | AC (cum.) Actual Cost
# | Task Descriptions | Responsible | Status Date | %Complete | Start Date | Finish Date | Lhrs or NL$ | Lrate or NL$ | Actual Costs | Labor + NonL $ | WS | EV | AC | SV | CV | WS Cum$ | EV Cum$ | AC Cum$ | STATUS | BAC | WS | EV | AC | SV | CV
1 | Purchase Items for Power Facility construction | Purchasing | 2018-01-01 | 50% | 2018-01-05 | 2018-01-10 | 0 | 25000 | 35000 | 25000 | 24.39% | 12.19% | 34.14% | -12.19% | -21.95% | 25000 | 12500 | 35000 | 2018-01-01 | 102510 | 25000 | 12500 | 35000 | -12500 | -22500
2 | File and receive permits | Project Team A1 | 2018-02-27 | 35% | 2018-01-10 | 2018-01-31 | 16 | 100 | 3200 | 1600 | 25.95% | 12.74% | 37.26% | -13.21% | -24.52% | 26600 | 13060 | 38200 | 2018-02-27 | 102510 | 26600 | 13060 | 38200 | -13540 | -25140
3 | Prepare foundation | Supplier Alpha | 2018-03-31 | 10% | 2018-02-01 | 2018-02-05 | 24 | 35 | 1100 | 840 | 26.77% | 12.82% | 38.34% | -13.95% | -25.52% | 27440 | 13144 | 39300 | 2018-03-31 | 102510 | 27440 | 13144 | 39300 | -14296 | -26156
4 | Pour cement for foundation | Supplier Alpha |  |  | 2018-02-06 | 2018-03-01 | 16 | 35 |  | 560 | 27.31% | 12.82% | 38.34% |  |  | 28000 |  | 39300
5 | Construct building frame, including doors and windows | Supplier Bravo |  |  | 2018-02-08 | 2018-03-31 | 512 | 55 |  | 28160 | 54.78% | 12.82% | 38.34% |  |  | 56160 |  | 39300
6 | Construct building roof | Supplier Bravo |  |  | 2018-03-11 | 2018-04-02 | 144 | 55 |  | 7920 | 62.51% | 12.82% | 38.34% |  |  | 64080 |  | 39300
7 | Install electric wiring, lights and panels | Supplier Charlie |  |  | 2018-03-21 | 2018-05-05 | 56 | 75 |  | 4200 | 66.61% | 12.82% | 38.34% |  |  | 68280 |  | 39300
8 | Install water and plumbing | Supplier Delta | 7EmES5u21 |  | 2018-03-29 | 2018-06-15 | 256 | 65 |  | 16640 | 82.84% | 12.82% | 38.34% |  |  | 84920 |  | 39300
9 | Install Drywall | Supplier Bravo |  |  | 2018-04-16 | 2018-07-20 | 48 | 55 |  | 2640 | 85.42% | 12.82% | 38.34% |  |  | 87560 |  | 39300
10 | Install floor and ceilings | Supplier Bravo |  |  | 2018-04-21 | 2018-08-15 | 128 | 55 |  | 7040 | 92.28% | 12.82% | 38.34% |  |  | 94600 |  | 39300
11 | Paint and finish | Supplier Bravo |  |  | 2018-04-20 | 2018-09-10 | 42 | 55 |  | 2310 | 94.54% | 12.82% | 38.34% |  |  | 96910 |  | 39300
12 | Install fixtures for power equipment | Supplier Charlie |  |  | 2018-04-26 | 2018-10-02 | 64 | 75 |  | 4800 | 99.22% | 12.82% | 38.34% |  |  | 101710 |  | 39300
13 | Building ready for power equipment installation | Project Team A1 |  |  | 2018-05-01 | 2018-10-05 | 8 | 100 |  | 800 | 100% | 12.82% | 38.34% |  |  | 102510 |  | 39300
14
15 | bar: -14296 C to 0.47901 J
16
17 | bar: -14296 C to 0.47901 J
18
19 | bar: -14296 C to 0.47901 J
20
21 | bar: -14296 C to 0.47901 J
22
23 | bar: -14296 C to 0.47901 J
24
25 | bar: -14296 C to 0.47901 J
26
27 | bar: -14296 C to 0.47901 J
28
29 | bar: -14296 C to 0.47901 J
30
31 | bar: -14296 C to 0.47901 J
32
33 | bar: -14296 C to 0.47901 J
34
35 | bar: -14296 C to 0.47901 J
36
37 | bar: -14296 C to 0.47901 J
38
39 | bar: -14296 C to 0.47901 J
40
41 | bar: -14296 C to 0.47901 J
42
43 | bar: -14296 C to 0.47901 J
44
45 | bar: -14296 C to 0.47901 J
46
47 | bar: -14296 C to 0.47901 J
48
49 | bar: -14296 C to 0.47901 J
50
51 | bar: -14296 C to 0.47901 J
52
53 | bar: -14296 C to 0.47901 J
54
55 | bar: -14296 C to 0.47901 J
56
57 | bar: -14296 C to 0.47901 J
58
59 | bar: -14296 C to 0.47901 J
60
61 | bar: -14296 C to 0.47901 J
62
63 | bar: -14296 C to 0.47901 J
64
65 | bar: -14296 C to 0.47901 J
66
67 | bar: -14296 C to 0.47901 J
68
69 | bar: -14296 C to 0.47901 J
70
71 | bar: -14296 C to 0.47901 J
72
73 | bar: -14296 C to 0.47901 J
74
75 | bar: -14296 C to 0.47901 J
76
77 | bar: -14296 C to 0.47901 J
78
79 | bar: -14296 C to 0.47901 J
80
81 | bar: -14296 C to 0.47901 J
82
83 | bar: -14296 C to 0.47901 J
84
85 | bar: -14296 C to 0.47901 J
86
87 | bar: -14296 C to 0.47901 J
88
89 | bar: -14296 C to 0.47901 J
90
91 | bar: -14296 C to 0.47901 J
92
93 | bar: -14296 C to 0.47901 J
94
95 | bar: -14296 C to 0.47901 J
96
97 | bar: -14296 C to 0.47901 J
98
99 | bar: -14296 C to 0.47901 J
100
505500
Formulas:
STATUS = IF([E]=0,"",([D]))

## Elafino DetailedPlan
| Project Title: | Dance Sport Rink3 |  |  |  | ANALYSIS NOTES
| Project ID: | LFT-3 |  |  | 1
| Project Manager: | John Wayne |  |  | 2
| Project Control: | Annie Oakley |  |  | 3
| Project Status Date: | 2012-04-30 |  |  | 4
| Planned Finished Date | 2012-05-31 |  |  | 5
New Forcasted Finished Date
| Budget At Completion (BAC) | 741100 | PM Estimate: | 775000
| EV Cumulative to Date: | 567550
| AC Cumulative to Date: | 593100
| WS Cumulative to Date: | 672100
| Cost Variance (EV - AC) | -25550 | CPI | 0.95692
| Schedule Variance (EV - WS) | -104550 | SPI | 0.84444
A | PROJECT DESCRIPTION | C | D | E | F | G | H | I | J | K | L | M | N | O | P | Q | R | S
| The XYZ Power Facility is a special building for local housing street lights and a new security alarm camera and storm warning siren system that meets Dept of Homeland Security Spec No. 4xx21alp12 | Responsible for Task | Input Status Date | Input Percent Completed (EV) | Input Planned Start Date | Input Estimated Finish Date | Input Planned LABOR hours or "0" of Non-Labor (Material, other) | Input Labor Rate/Hours or Non-Labor Dollars ($) | Input Actual Costs from Accounting Records | BAC (Budget-At- Completion) | WS Work Scheduled | EV Earned Value | AC Actual Cost | SV = (EV-WS) | CV = (EV-AC) | WS Work Scheduled $ | EV Earned Value ($) | AC (cum.) Actual Cost
# | Task Descriptions | Responsible | Status Date | %Complete | Start Date | Finish Date | Lhrs or NL$ | Lrate or NL$ | Actual Costs | Labor + NonL $ | WS | EV | AC | SV | CV | WS Cum$ | EV Cum$ | AC Cum$ | STATUS | BAC | WS | EV | AC | SV | CV
1 | Purchase Items for Dance Sport Rink construction | Purchasing | 2012-01-31 | 100% | 2012-01-05 | 2012-01-10 | 0 | 25000 | 25000 | 25000 | 3.373% | 3.373% | 3.373% | 0% | 0% | 25000 | 25000 | 25000 | 2012-01-31 | 741100 | 25000 | 25000 | 25000 | 0 | 0
2 | File and receive permits | Project Team A1 | 2012-01-31 | 100% | 2012-01-10 | 2012-01-31 | 16 | 100 | 1600 | 1600 | 3.589% | 3.589% | 3.589% | 0% | 0% | 26600 | 26600 | 26600 | 2012-01-31 | 741100 | 26600 | 26600 | 26600 | 0 | 0
3 | Award contract to supplier Alpha (rink construction) | Supplier Alpha | 2012-02-27 | 100% | 2012-02-01 | 2012-02-05 | 0 | 125000 | 157000 | 125000 | 20.46% | 20.46% | 24.77% | 0% | -4.318% | 151600 | 151600 | 183600 | 2012-02-27 | 741100 | 151600 | 151600 | 183600 | 0 | -32000
4 | Award contract to supplier Bravo (rink equipment) | Supplier Alpha | 2012-02-27 | 100% | 2012-02-06 | 2012-02-07 | 0 | 52000 | 52000 | 52000 | 27.47% | 27.47% | 31.79% | 0% | -4.318% | 203600 | 203600 | 235600 | 2012-02-27 | 741100 | 203600 | 203600 | 235600 | 0 | -32000
5 | Award contract to supplier Charlie (rink electronics) | Supplier Bravo | 2012-03-31 | 100% | 2012-02-08 | 2012-03-10 | 0 | 75000 | 75000 | 75000 | 37.59% | 37.59% | 41.91% | 0% | -4.318% | 278600 | 278600 | 310600 | 2012-03-31 | 741100 | 278600 | 278600 | 310600 | 0 | -32000
6 | Assemble rink equipment | Supplier Bravo | 2012-03-31 | 100% | 2012-03-11 | 2012-03-20 | 9 | 25000 | 25000 | 225000 | 67.95% | 67.95% | 45.28% | 0% | 22.67% | 503600 | 503600 | 335600 | 2012-03-31 | 741100 | 503600 | 503600 | 335600 | 0 | 168000
7 | Install electric wiring, lights and panels | Supplier Charlie | 2012-03-31 | 100% | 2012-03-21 | 2012-03-28 | 0 | 35000 | 92500 | 35000 | 72.68% | 72.68% | 57.77% | 0% | 14.91% | 538600 | 538600 | 428100 | 2012-03-31 | 741100 | 538600 | 538600 | 428100 | 0 | 110500
8 | Install rink electronics | Supplier Charlie | 2012-04-30 | 50% | 2012-03-29 | 2012-04-15 | 0 | 39000 | 45000 | 39000 | 77.94% | 75.31% | 63.84% | -2.631% | 11.47% | 577600 | 558100 | 473100 | 2012-04-30 | 741100 | 577600 | 558100 | 473100 | -19500 | 85000
9 | Install rink flooring for dancers and competition | Supplier Bravo | 2012-04-30 | 10% | 2012-04-16 | 2012-04-20 | 0 | 94500 | 120000 | 94500 | 90.69% | 76.58% | 80.03% | -14.11% | -3.448% | 672100 | 567550 | 593100 | 2012-04-30 | 741100 | 672100 | 567550 | 593100 | -104550 | -25550
10 | Install updates to wall murals, stands and cosmetics | Supplier Bravo |  | 0% | 2012-04-21 | 2012-04-29 | 0 | 35000 | 0 | 35000 | 95.41% | 76.58% | 80.03% |  |  | 707100 |  | 593100
11 | Paint and finish | Supplier Bravo |  | 0% | 2012-04-20 | 2012-04-25 | 0 | 15000 | 0 | 15000 | 97.44% | 76.58% | 80.03% |  |  | 722100 |  | 593100
12 | Test all equipment, electronics and dancefloor elements | Supplier Charlie |  | 0% | 2012-04-26 | 2012-04-30 | 0 | 15000 | 0 | 15000 | 99.46% | 76.58% | 80.03% |  |  | 737100 |  | 593100
13 | Rink 3 acceptance inspection | Project Team A1 |  | 0% | 2012-05-01 | 2012-05-01 | 40 | 100 | 0 | 4000 | 100% | 76.58% | 80.03% |  |  | 741100 |  | 593100
14
15 | bar: -104550 C to 0.84444 J
16
17 | bar: -104550 C to 0.84444 J
18
19 | bar: -104550 C to 0.84444 J
20
21 | bar: -104550 C to 0.84444 J
22
23 | bar: -104550 C to 0.84444 J
24
25 | bar: -104550 C to 0.84444 J
26
27 | bar: -104550 C to 0.84444 J
28
29 | bar: -104550 C to 0.84444 J
30
31 | bar: -104550 C to 0.84444 J
32
33 | bar: -104550 C to 0.84444 J
34
35 | bar: -104550 C to 0.84444 J
36
37 | bar: -104550 C to 0.84444 J
38
39 | bar: -104550 C to 0.84444 J
40
41 | bar: -104550 C to 0.84444 J
42
43 | bar: -104550 C to 0.84444 J
44
45 | bar: -104550 C to 0.84444 J
46
47 | bar: -104550 C to 0.84444 J
48
49 | bar: -104550 C to 0.84444 J
50
51 | bar: -104550 C to 0.84444 J
52
53 | bar: -104550 C to 0.84444 J
54
55 | bar: -104550 C to 0.84444 J
56
57 | bar: -104550 C to 0.84444 J
58
59 | bar: -104550 C to 0.84444 J
60
61 | bar: -104550 C to 0.84444 J
62
63 | bar: -104550 C to 0.84444 J
64
65 | bar: -104550 C to 0.84444 J
66
67 | bar: -104550 C to 0.84444 J
68
69 | bar: -104550 C to 0.84444 J
70
71 | bar: -104550 C to 0.84444 J
72
73 | bar: -104550 C to 0.84444 J
74
75 | bar: -104550 C to 0.84444 J
76
77 | bar: -104550 C to 0.84444 J
78
79 | bar: -104550 C to 0.84444 J
80
81 | bar: -104550 C to 0.84444 J
82
83 | bar: -104550 C to 0.84444 J
84
85 | bar: -104550 C to 0.84444 J
86
87 | bar: -104550 C to 0.84444 J
88
89 | bar: -104550 C to 0.84444 J
90
91 | bar: -104550 C to 0.84444 J
92
93 | bar: -104550 C to 0.84444 J
94
95 | bar: -104550 C to 0.84444 J
96
97 | bar: -104550 C to 0.84444 J
98
99 | bar: -104550 C to 0.84444 J
100
4983700
Formulas:
STATUS = IF([E]=0,"",([D]))