## Title
OFT 6.1d Risk Manager™
Copyright © 2000 to 2019 AfCI LLC All Rights Reserved
OE21 Continuous Improvement Tool (Version 2019)
Warning: This computer program is protected by copyright law in the United States and international treaties including the Berne Convention. Unauthorized reproduction or distribution of this program, or any portion of it, may result in severe civil and criminal penalties, and will be prosecuted to the maximum extent possible under the law. For each instance in which a United States Court finds that infringement was committed willfully, the court in its discretion may increase the award of statutory damages to a sum of not more than $150,000.

## Risk Matrix
Risk No. | Related Risk No. | Responsible Team | RISK Title | Timeframe Start | Timeframe End | Impact (1-5) | Probability (%) | Risk Rank (formula) | Manage/Mitigate Plan | Action Plan Responsibility | Action Plan Start | Action Plan Finish | Action Plan % Completed | NOTES (Risk Triggers or other important notes useful in risk detection and management | Risk Rank threshold low negligible | Risk Rank threshold hi minor | Risk Rank threshold low marginal | Risk Rank threshold hi serious | Risk Rank threshold low critical | Risk Rank threshold hi catastrophic
[7 empty] | Target>> | 0.005 | Target should be near zero (.005)
[7 empty] | Score>> |  | Score is average of all rows in Column I and should be at or below Target Value
1 | [14 empty] | 1e-10 | 0.5 | 0.5 | 3 | 3 | 5
2 | [14 empty] | edit above cell | edit above cell | edit above cell | edit above cell | edit above cell | edit above cell
3
4
5 | [14 empty] | 1e-10 | 0.5 | 0.5 | 3 | 3 | 5
6 | [14 empty] | original value | original value | original value | original value | original value | original value
7
8
9
10
11
12
Note on I1: Set thresholds in cells P2 to U2

## Example1
Risk No. | Related Risk No. | Responsible Team | RISK Title | Timeframe Start | Timeframe End | Impact (1-5) | Probability (%) | Risk Rank (formula) | Manage/Mitigate Plan | Action Plan Responsibility | Action Plan Start | Action Plan Finish | Action Plan % Completed | NOTES (Risk Triggers or other important notes useful in risk detection and management | Risk Rank threshold low negligible | Risk Rank threshold hi minor | Risk Rank threshold low marginal | Risk Rank threshold hi serious | Risk Rank threshold low critical | Risk Rank threshold hi catastrophic
[7 empty] | Target>> | 0.005 | Target should be near zero (.005)
[7 empty] | Score>> | 1.5917 | Score is average of all rows in Column I and should be at or below Target Value
A1 |  | OFT | visitor falls down | 2007-10-01 | 2008-09-30 | 5 | 90% | 4.5 | Apply non-slip paint or wax; ice warning signs | Ed Smith | 2007-10-01 | 2007-12-20 | 10% | Online or email notices about program funding are useful triggers | 1e-10 | 0.5 | 0.5 | 3 | 3 | 5
A3 |  | OFT | child offender finds victum in facility | 2007-10-01 | 2008-09-30 | 4 | 70% | 2.8 | Control access with MIS ID check database | Ed Smith | 2007-10-01 | 2007-12-20 | 10% | Online or email notices about program funding are useful triggers | edit above cell | edit above cell | edit above cell | edit above cell | edit above cell | edit above cell
A5 |  | OFT | utilities fail; ice melts | 2007-10-01 | 2008-09-30 | 3 | 50% | 1.5 | Add backup generators for ice rinks | Jay Thomas | 2007-10-01 | 2008-02-15 | 15% | Activity progress toward milestone 1 indicates probability of milestone begin on time
A2 |  | OFT | crime in parking areas | 2007-10-01 | 2008-09-30 | 2 | 30% | 0.6 | Add lights and security patrols as needed | Jay Thomas | 2007-10-01 | 2008-02-15 | 15% | Activity progress toward milestone 1 indicates probability of milestone begin on time
A4 |  | CFT | better sports facility opens nearby | 2007-10-01 | 2008-09-30 | 1 | 10% | 0.1 | Study competitor offerings; innovate | Susan Michelle | 2007-10-01 | 2007-11-15 | 2% | Internal fire inspection reports are early indicators | 1e-10 | 0.5 | 0.5 | 3 | 3 | 5
A6 | A4 | WFT | competitor recruits key instructors | 2007-10-01 | 2008-09-30 | 1 | 5% | 0.05 | Keep workforce satisfied and motivated | Kellie Smith | 2007-10-01 | 2007-12-10 | 25% | Network indicators of attempted hacker intrusions should be critical trigger | original value | original value | original value | original value | original value | original value
Note on I1: Set thresholds in cells P2 to U2

## Example2
Risk No. | Related Risk No. | Responsible Team | RISK Title | Timeframe Start | Timeframe End | Impact (1-5) | Probability (%) | Risk Rank (formula) | Manage/Mitigate Plan | Action Plan Responsibility | Action Plan Start | Action Plan Finish | Action Plan % Completed | NOTES (Risk Triggers or other important notes useful in risk detection and management | Risk Rank threshold low negligible | Risk Rank threshold hi minor | Risk Rank threshold low marginal | Risk Rank threshold hi serious | Risk Rank threshold low critical | Risk Rank threshold hi catastrophic
[7 empty] | Target>> | 0.005 | Target should be near zero (.005)
[7 empty] | Score>> | 2.03 | Score is average of all rows in Column I and should be at or below Target Value
1 |  | OFT | Hurricanes | 2019-01-01 | 2019-12-31 | 5 | 65% | 3.25 | https://www.ready.gov/hurricanes | OFT (Name) | 2019-02-01 | 2019-02-28 | 25% | ACTUAL Media reports of hurricanes that may impact our organization are coming in now | 1e-10 | 0.5 | 0.5 | 3 | 3 | 5
2 | 2 | OFT | Tornadoes | 2019-01-01 | 2019-12-31 | 5 | 35% | 1.75 | https://www.ready.gov/tornadoes | OFT (Name) | 2019-03-01 | 2019-03-31 |  | Media reports of hurricanes that may impact our organization. Tornados are normally events that accompany Hurricanes in our east coast Florida location | edit above cell | edit above cell | edit above cell | edit above cell | edit above cell | edit above cell
3 | 2 | OFT | Floods | 2019-01-01 | 2019-12-31 | 4 | 40% | 1.6 | https://www.ready.gov/floods | OFT (Name) | 2019-04-01 | 2019-04-30 |  | Media reports of hurricanes that may impact our organization. Flooding and storm surges are common events that accompany Hurricanes in our east coast Florida location
4 |  | OFT | Cybersecurity | 2019-01-01 | 2019-12-31 | 5 | 35% | 1.75 | https://www.ready.gov/cybersecurity | OFT (Name) | 2019-05-01 | 2019-05-31 |  | Media and web-based reports of cyber-attacks on organization similar to Sports Centers
5 | 2 | OFT | Power Outages | 2019-01-01 | 2019-12-31 | 3 | 60% | 1.8 | https://www.ready.gov/power-outages | OFT (Name) | 2019-06-01 | 2019-06-30 |  | Media reports of severe thunderstorms, hurricanes, tornados are common events that cause power outages. Local power company reports or alerts are other triggers. | 1e-10 | 0.5 | 0.5 | 3 | 3 | 5
6 | [14 empty] | original value | original value | original value | original value | original value | original value
7
8
9
10
11
12
Note on I1: Set thresholds in cells P2 to U2