## Title
WFT Workforce Excellence Strategy Plan V21™
Copyright © 2000 to 2020 AfCI LLC All Rights Reserved
OE21 Continuous Improvement Tool (WFT v.21)
Warning: This computer program is protected by copyright law in the United States and international treaties including the Berne Convention. Unauthorized reproduction or distribution of this program, or any portion of it, may result in severe civil and criminal penalties, and will be prosecuted to the maximum extent possible under the law. For each instance in which a United States Court finds that infringement was committed willfully, the court in its discretion may increase the award of statutory damages to a sum of not more than $150,000.

## SimplePlan
Project Title:
Project ID:
Project Manager:
Project Control:
Planned Start Date
Planned Finished Date
| Budget At Completion (Contract Target Cost) | 0
A | PROJECT DESCRIPTION | C | D | E | F | G | H | I | J | K
|  | Responsible for Task | Input Status Date | Input Percent Completed (EV) | Input Planned Start Date | Input Estimated Finish Date | Input Planned LABOR hours or "0" of Non-Labor (Material, other) | Input Labor Rate/Hours or Non-Labor Dollars ($) | Input Actual Costs from Accounting Records | BAC (Budget-At- Completion)
# | Task Descriptions | Responsible | Status Date | %Complete | Start Date | Finish Date | Lhrs or NL$ | Lrate or NL$ | Actual Costs | Labor + NonL $
1 | bar: C to J
2
3 | bar: C to J
4
5 | bar: C to J
6
7 | bar: C to J
8
9 | bar: C to J
10
11 | bar: C to J
12
13 | bar: C to J
14
15 | bar: C to J
16
17 | bar: C to J
18
19 | bar: C to J
20
21 | bar: C to J
22
23 | bar: C to J
24
25 | bar: C to J
26
27 | bar: C to J
28
29 | bar: C to J
30
31 | bar: C to J
32
33 | bar: C to J
34
35 | bar: C to J
36
37 | bar: C to J
38
39 | bar: C to J
40
41 | bar: C to J
42
43 | bar: C to J
44
45 | bar: C to J
46
47 | bar: C to J
48
49 | bar: C to J
50
51 | bar: C to J
52
53 | bar: C to J
54
55 | bar: C to J
56
57 | bar: C to J
58
59 | bar: C to J
60
61 | bar: C to J
62
63 | bar: C to J
64
65 | bar: C to J
66
67 | bar: C to J
68
69 | bar: C to J
70
71 | bar: C to J
72
73 | bar: C to J
74
75 | bar: C to J
76
77 | bar: C to J
78
79 | bar: C to J
80
81 | bar: C to J
82
83 | bar: C to J
84
85 | bar: C to J
86
87 | bar: C to J
88
89 | bar: C to J
90
91 | bar: C to J
92
93 | bar: C to J
94
95 | bar: C to J
96
97 | bar: C to J
98
99 | bar: C to J
100

## DetailedPlan
| Project Title: | Workforce Excellence |  |  |  | ANALYSIS NOTES
| Project ID: | WFT01 |  |  | 1
| Project Manager: | Dee Benefito |  |  | 2
| Project Control: | Semour Bits |  |  | 3
| Project Status Date: | 2019-04-02 |  |  | 4
| Planned Finished Date | 2019-05-23 |  |  | 5
| New Forcasted Finished Date | 2019-06-10
| Budget At Completion (BAC) | 3934 | PM Estimate: | 7000
| EV Cumulative to Date: | 3406
| AC Cumulative to Date: | 5860
| WS Cumulative to Date: | 3934
| Cost Variance (EV - AC) | -2454 | CPI | 0.58123
| Schedule Variance (EV - WS) | -528 | SPI | 0.86579
A | PROJECT DESCRIPTION | C | D | E | F | G | H | I | J | K | L | M | N | O | P | Q | R | S
|  | Responsible for Task | Input Status Date | Input Percent Completed (EV) | Input Planned Start Date | Input Estimated Finish Date | Input Planned LABOR hours or "0" of Non-Labor (Material, other) | Input Labor Rate/Hours or Non-Labor Dollars ($) | Input Actual Costs from Accounting Records | BAC (Budget-At- Completion) | WS Work Scheduled | EV Earned Value | AC Actual Cost | SV = (EV-WS) | CV = (EV-AC) | WS Work Scheduled $ | EV Earned Value ($) | AC (cum.) Actual Cost
# | Task Descriptions | Responsible | Status Date | %Complete | Start Date | Finish Date | Lhrs or NL$ | Lrate or NL$ | Actual Costs | Labor + NonL $ | WS | EV | AC | SV | CV | WS Cum$ | EV Cum$ | AC Cum$ | STATUS | BAC | WS | EV | AC | SV | CV
1 | Conduct Workforce Satisfaction Assessment | WFT | 2019-04-30 | 100% | 2019-04-02 | 2019-04-15 | 10 | 35 | 350 | 350 | 8.897% | 8.897% | 8.897% | 0% | 0% | 350 | 350 | 350 | 2019-04-30 | 3934 | 350 | 350 | 350 | 0 | 0
2 | Balance workload for overloaded units | WFT | 2019-04-30 | 100% | 2019-04-21 | 2019-04-23 | 16 | 35 | 500 | 560 | 23.13% | 23.13% | 21.61% | 0% | 1.525% | 910 | 910 | 850 | 2019-04-30 | 3934 | 910 | 910 | 850 | 0 | 60
3 | Pinpoint reasons for turnover | WFT | 2019-04-30 | 100% | 2019-04-24 | 2018-04-27 | 16 | 22 | 250 | 352 | 32.08% | 32.08% | 27.96% | 0% | 4.118% | 1262 | 1262 | 1100 | 2019-04-30 | 3934 | 1262 | 1262 | 1100 | 0 | 162
4 | Create reward s for low or no absenteeism workers | WFT | 2019-04-30 | 100% | 2019-04-15 | 2019-05-01 | 16 | 35 | 500 | 560 | 46.31% | 46.31% | 40.67% | 0% | 5.643% | 1822 | 1822 | 1600 | 2019-04-30 | 3934 | 1822 | 1822 | 1600 | 0 | 222
5 | Implement accident prevention program | WFT | 2019-05-31 | 80% | 2019-04-23 | 2019-05-20 | 80 | 22 | 1760 | 1760 | 91.05% | 82.1% | 85.41% | -8.948% | -3.305% | 3582 | 3230 | 3360 | 2019-05-31 | 3934 | 3582 | 3230 | 3360 | -352 | -130
6 | Setup a better complaint process | WFT | 2019-05-31 | 50% | 2019-05-10 | 2019-05-23 | 16 | 22 | 2500 | 352 | 100% | 86.58% | 149% | -13.42% | -62.38% | 3934 | 3406 | 5860 | 2019-05-31 | 3934 | 3934 | 3406 | 5860 | -528 | -2454
7 | bar: -528 C to 0.86579 J
8
9 | bar: -528 C to 0.86579 J
10
11 | bar: -528 C to 0.86579 J
12
13 | bar: -528 C to 0.86579 J
14
15 | bar: -528 C to 0.86579 J
16
17 | bar: -528 C to 0.86579 J
18
19 | bar: -528 C to 0.86579 J
20
21 | bar: -528 C to 0.86579 J
22
23 | bar: -528 C to 0.86579 J
24
25 | bar: -528 C to 0.86579 J
26
27 | bar: -528 C to 0.86579 J
28
29 | bar: -528 C to 0.86579 J
30
31 | bar: -528 C to 0.86579 J
32
33 | bar: -528 C to 0.86579 J
34
35 | bar: -528 C to 0.86579 J
36
37 | bar: -528 C to 0.86579 J
38
39 | bar: -528 C to 0.86579 J
40
41 | bar: -528 C to 0.86579 J
42
43 | bar: -528 C to 0.86579 J
44
45 | bar: -528 C to 0.86579 J
46
47 | bar: -528 C to 0.86579 J
48
49 | bar: -528 C to 0.86579 J
50
51 | bar: -528 C to 0.86579 J
52
53 | bar: -528 C to 0.86579 J
54
55 | bar: -528 C to 0.86579 J
56
57 | bar: -528 C to 0.86579 J
58
59 | bar: -528 C to 0.86579 J
60
61 | bar: -528 C to 0.86579 J
62
63 | bar: -528 C to 0.86579 J
64
65 | bar: -528 C to 0.86579 J
66
67 | bar: -528 C to 0.86579 J
68
69 | bar: -528 C to 0.86579 J
70
71 | bar: -528 C to 0.86579 J
72
73 | bar: -528 C to 0.86579 J
74
75 | bar: -528 C to 0.86579 J
76
77 | bar: -528 C to 0.86579 J
78
79 | bar: -528 C to 0.86579 J
80
81 | bar: -528 C to 0.86579 J
82
83 | bar: -528 C to 0.86579 J
84
85 | bar: -528 C to 0.86579 J
86
87 | bar: -528 C to 0.86579 J
88
89 | bar: -528 C to 0.86579 J
90
91 | bar: -528 C to 0.86579 J
92
93 | bar: -528 C to 0.86579 J
94
95 | bar: -528 C to 0.86579 J
96
97 | bar: -528 C to 0.86579 J
98
99 | bar: -528 C to 0.86579 J
100
13120
Formulas:
STATUS = IF([E]=0,"",([D]))
Note on C19: Insert title or code of the performing organization who will accomplish the task.
Note on G19: Insert date that task should be finished.
Note on H19: IF task requires labor hours, insert hours to do the task. IF task requires non-labor costs, insert a zero (0) in this cell.
Note on I19: IF task requires labor, insert labor hourly rate; IF task is non-labor insert dollar amount.

## SimplePlan Example
| Project Title: | Workforce Environment
| Project ID: | WFT01
| Project Manager: | Dee Benefito
| Project Control: | Semour Bits
| Planned Start Date | 2019-04-02
| Planned Finished Date | 2019-09-02
| Budget At Completion (BAC) | 67264
A | PROJECT DESCRIPTION | C | D | E | F | G | H | I | J | K
| WORKFORCE ENVIRONMENT IMPROVEMENT - Based on low ratings of workforce satisfaciton, and less than desired estimates of workforce capacity. | Responsible for Task | Input Status Date | Input Percent Completed (EV) | Input Planned Start Date | Input Estimated Finish Date | Input Planned LABOR hours or "0" of Non-Labor (Material, other) | Input Labor Rate/Hours or Non-Labor Dollars ($) | Input Actual Costs from Accounting Records | BAC (Budget-At- Completion)
# | Task Descriptions | Responsible | Status Date | %Complete | Start Date | Finish Date | Lhrs or NL$ | Lrate or NL$ | Actual Costs | Labor + NonL $
1 | Conduct Workforce Satisfaction Assessment | WFT |  |  | 2019-04-02 | 2019-04-15 | 10 | 35 |  | 350
2 | Balance workload for overloaded units | WFT |  |  | 2019-04-21 | 2019-04-23 | 16 | 35 |  | 560
3 | Pinpoint reasons for turnover | WFT |  |  | 2019-04-24 | 2018-04-27 | 16 | 22 |  | 352
4 | Create reward s for low or no absenteeism workers | WFT |  |  | 2019-04-15 | 2019-05-01 | 16 | 35 |  | 560
5 | Implement accident prevention program | WFT |  |  | 2019-04-23 | 2019-05-20 | 80 | 22 |  | 1760
6 | Setup a better complaint process | WFT |  |  | 2019-05-10 | 2019-05-23 | 16 | 22 |  | 352
7 | Purchase a performance rewards system (software) | OFT |  |  | 2019-06-01 | 2019-06-01 | 0 | 12500 |  | 12500
8 | Measure Improvement (Engagement/Satisfaction) | WFT |  |  | 2019-06-01 | 2019-06-02 | 8 | 35 |  | 280
9 | Test 1 - Improved Workforce Engagement/Satisfaction | WFT |  |  | 2019-05-15 | 2019-06-09 | 40 | 35 |  | 1400
10 | Conduct Workforce Capability Assessment | WFT |  |  | 2019-06-08 | 2019-06-10 | 8 | 35 |  | 280
11 | Identify low performers | WFT |  |  | 2019-06-08 | 2019-06-11 | 2 | 35 |  | 70
12 | Create plan to improve low performers | WFT |  |  | 2019-06-10 | 2019-06-13 | 16 | 35 |  | 560
13 | Identify worker capability for DanceSport service | WFT |  |  | 2019-06-12 | 2019-06-21 | 40 | 35 |  | 1400
14 | Measure Improvement (workforce capability) | WFT |  |  | 2019-06-21 | 2019-06-22 | 8 | 35 |  | 280
15 | Test 2 - Improved Workforce Capacity | WFT |  |  | 2019-06-15 | 2019-06-30 | 40 | 35 |  | 1400
16 | Conduct workforce capacity assessment | WFT |  |  | 2019-06-28 | 2019-07-01 | 8 | 35 |  | 280
17 | Identify workforce capacity needs | WFT |  |  | 2019-06-28 | 2019-07-09 | 40 | 35 |  | 1400
18 | Re-train existing workforce to meet capacity needs | WFT |  |  | 2019-06-20 | 2019-09-01 | 320 | 35 |  | 11200
19 | Recruit new workers to meet current capacity needs | OFT |  |  | 2019-06-22 | 2019-09-15 | 320 | 65 |  | 20800
20 | Recruit DanceSport workforce to meet future needs | WFT |  |  | 2019-06-25 | 2019-09-30 | 320 | 35 |  | 11200
21 | Measure Improvement (workforce capacity) | WFT |  |  | 2019-06-28 | 2019-10-01 | 8 | 35 |  | 280
22
23 | bar: C to J
24
25 | bar: C to J
26
27 | bar: C to J
28
29 | bar: C to J
30
31 | bar: C to J
32
33 | bar: C to J
34
35 | bar: C to J
36
37 | bar: C to J
38
39 | bar: C to J
40
41 | bar: C to J
42
43 | bar: C to J
44
45 | bar: C to J
46
47 | bar: C to J
48
49 | bar: C to J
50
51 | bar: C to J
52
53 | bar: C to J
54
55 | bar: C to J
56
57 | bar: C to J
58
59 | bar: C to J
60
61 | bar: C to J
62
63 | bar: C to J
64
65 | bar: C to J
66
67 | bar: C to J
68
69 | bar: C to J
70
71 | bar: C to J
72
73 | bar: C to J
74
75 | bar: C to J
76
77 | bar: C to J
78
79 | bar: C to J
80
81 | bar: C to J
82
83 | bar: C to J
84
85 | bar: C to J
86
87 | bar: C to J
88
89 | bar: C to J
90
91 | bar: C to J
92
93 | bar: C to J
94
95 | bar: C to J
96
97 | bar: C to J
98
99 | bar: C to J
100
Note on C19: Insert title or code of the performing organization who will accomplish the task.
Note on G19: Insert date that task should be finished.
Note on H19: IF task requires labor hours, insert hours to do the task. IF task requires non-labor costs, insert a zero (0) in this cell.
Note on I19: IF task requires labor, insert labor hourly rate; IF task is non-labor insert dollar amount.

## DetailedPlan Example
| Project Title: | Workforce Excellence |  |  |  | ANALYSIS NOTES
| Project ID: | WFT01 |  |  | 1
| Project Manager: | Dee Benefito |  |  | 2
| Project Control: | Semour Bits |  |  | 3
| Project Status Date: | 2019-04-02 |  |  | 4
| Planned Finished Date | 2019-09-02 |  |  | 5
| New Forcasted Finished Date | 2019-09-02
| Budget At Completion (BAC) | 67264 | PM Estimate: | 67264
| EV Cumulative to Date: | 3405
| AC Cumulative to Date: | 5860
| WS Cumulative to Date: | 3934
| Cost Variance (EV - AC) | -2455 | CPI | 0.58106
| Schedule Variance (EV - WS) | -529 | SPI | 0.86553
A | PROJECT DESCRIPTION | C | D | E | F | G | H | I | J | K | L | M | N | O | P | Q | R | S
| WORKFORCE ENVIRONMENT IMPROVEMENT - Based on low ratings of workforce satisfaciton, and less than desired estimates of workforce capacity. | Responsible for Task | Input Status Date | Input Percent Completed (EV) | Input Planned Start Date | Input Estimated Finish Date | Input Planned LABOR hours or "0" of Non-Labor (Material, other) | Input Labor Rate/Hours or Non-Labor Dollars ($) | Input Actual Costs from Accounting Records | BAC (Budget-At- Completion) | WS Work Scheduled | EV Earned Value | AC Actual Cost | SV = (EV-WS) | CV = (EV-AC) | WS Work Scheduled $ | EV Earned Value ($) | AC (cum.) Actual Cost
# | Task Descriptions | Responsible | Status Date | %Complete | Start Date | Finish Date | Lhrs or NL$ | Lrate or NL$ | Actual Costs | Labor + NonL $ | WS | EV | AC | SV | CV | WS Cum$ | EV Cum$ | AC Cum$ | STATUS | BAC | WS | EV | AC | SV | CV
1 | Conduct Workforce Satisfaction Assessment | WFT | 2019-04-30 | 100% | 2019-04-02 | 2019-04-15 | 10 | 35 | 350 | 350 | 0.5203% | 0.5203% | 0.5203% | 0% | 0% | 350 | 350 | 350 | 2019-04-30 | 67264 | 350 | 350 | 350 | 0 | 0
2 | Balance workload for overloaded units | WFT | 2019-04-30 | 100% | 2019-04-21 | 2019-04-23 | 16 | 35 | 500 | 560 | 1.353% | 1.353% | 1.264% | 0% | 0.0892% | 910 | 910 | 850 | 2019-04-30 | 67264 | 910 | 910 | 850 | 0 | 60
3 | Pinpoint reasons for turnover | WFT | 2019-04-30 | 100% | 2019-04-24 | 2018-04-27 | 16 | 22 | 250 | 352 | 1.876% | 1.876% | 1.635% | 0% | 0.2408% | 1262 | 1262 | 1100 | 2019-04-30 | 67264 | 1262 | 1262 | 1100 | 0 | 162
4 | Create reward s for low or no absenteeism workers | WFT | 2019-04-30 | 100% | 2019-04-15 | 2019-05-01 | 16 | 35 | 500 | 560 | 2.709% | 2.709% | 2.379% | 0% | 0.33% | 1822 | 1822 | 1600 | 2019-04-30 | 67264 | 1822 | 1822 | 1600 | 0 | 222
5 | Implement accident prevention program | WFT | 2019-05-31 | 80% | 2019-04-23 | 2019-05-20 | 80 | 22 | 1760 | 1760 | 5.325% | 4.802% | 4.995% | -0.5233% | -0.1933% | 3582 | 3230 | 3360 | 2019-05-31 | 67264 | 3582 | 3230 | 3360 | -352 | -130
6 | Setup a better complaint process | WFT | 2019-05-31 | 50% | 2019-05-10 | 2019-05-23 | 16 | 22 | 2500 | 352 | 5.849% | 5.064% | 8.712% | -0.785% | -3.648% | 3934 | 3406 | 5860 | 2019-05-31 | 67264 | 3934 | 3406 | 5860 | -528 | -2454
7 | Purchase a performance rewards system (software) | OFT |  |  | 2019-06-01 | 2019-06-01 | 0 | 12500 |  | 12500 | 24.43% | 5.064% | 8.712% |  |  | 16434 |  | 5860
8 | Measure Improvement (Engagement/Satisfaction) | WFT |  |  | 2019-06-01 | 2019-06-02 | 8 | 35 |  | 280 | 24.85% | 5.064% | 8.712% |  |  | 16714 |  | 5860
9 | Test 1 - Improved Workforce Engagement/Satisfaction | WFT |  |  | 2019-05-15 | 2019-06-09 | 40 | 35 |  | 1400 | 26.93% | 5.064% | 8.712% |  |  | 18114 |  | 5860
10 | Conduct Workforce Capability Assessment | WFT |  |  | 2019-06-08 | 2019-06-10 | 8 | 35 |  | 280 | 27.35% | 5.064% | 8.712% |  |  | 18394 |  | 5860
11 | Identify low performers | WFT |  |  | 2019-06-08 | 2019-06-11 | 2 | 35 |  | 70 | 27.45% | 5.064% | 8.712% |  |  | 18464 |  | 5860
12 | Create plan to improve low performers | WFT |  |  | 2019-06-10 | 2019-06-13 | 16 | 35 |  | 560 | 28.28% | 5.064% | 8.712% |  |  | 19024 |  | 5860
13 | Identify worker capability for DanceSport service | WFT |  |  | 2019-06-12 | 2019-06-21 | 40 | 35 |  | 1400 | 30.36% | 5.064% | 8.712% |  |  | 20424 |  | 5860
14 | Measure Improvement (workforce capability) | WFT |  |  | 2019-06-21 | 2019-06-22 | 8 | 35 |  | 280 | 30.78% | 5.064% | 8.712% |  |  | 20704 |  | 5860
15 | Test 2 - Improved Workforce Capacity | WFT |  |  | 2019-06-15 | 2019-06-30 | 40 | 35 |  | 1400 | 32.86% | 5.064% | 8.712% |  |  | 22104 |  | 5860
16 | Conduct workforce capacity assessment | WFT |  |  | 2019-06-28 | 2019-07-01 | 8 | 35 |  | 280 | 33.28% | 5.064% | 8.712% |  |  | 22384 |  | 5860
17 | Identify workforce capacity needs | WFT |  |  | 2019-06-28 | 2019-07-09 | 40 | 35 |  | 1400 | 35.36% | 5.064% | 8.712% |  |  | 23784 |  | 5860
18 | Re-train existing workforce to meet capacity needs | WFT |  |  | 2019-06-20 | 2019-09-01 | 320 | 35 |  | 11200 | 52.01% | 5.064% | 8.712% |  |  | 34984 |  | 5860
19 | Recruit new workers to meet current capacity needs | OFT |  |  | 2019-06-22 | 2019-09-15 | 320 | 65 |  | 20800 | 82.93% | 5.064% | 8.712% |  |  | 55784 |  | 5860
20 | Recruit DanceSport workforce to meet future needs | WFT |  |  | 2019-06-25 | 2019-09-30 | 320 | 35 |  | 11200 | 99.58% | 5.064% | 8.712% |  |  | 66984 |  | 5860
21 | Measure Improvement (workforce capacity) | WFT |  |  | 2019-06-28 | 2019-10-01 | 8 | 35 |  | 280 | 100% | 5.064% | 8.712% |  |  | 67264 |  | 5860
22
23 | bar: -529 C to 0.86553 J
24
25 | bar: -529 C to 0.86553 J
26
27 | bar: -529 C to 0.86553 J
28
29 | bar: -529 C to 0.86553 J
30
31 | bar: -529 C to 0.86553 J
32
33 | bar: -529 C to 0.86553 J
34
35 | bar: -529 C to 0.86553 J
36
37 | bar: -529 C to 0.86553 J
38
39 | bar: -529 C to 0.86553 J
40
41 | bar: -529 C to 0.86553 J
42
43 | bar: -529 C to 0.86553 J
44
45 | bar: -529 C to 0.86553 J
46
47 | bar: -529 C to 0.86553 J
48
49 | bar: -529 C to 0.86553 J
50
51 | bar: -529 C to 0.86553 J
52
53 | bar: -529 C to 0.86553 J
54
55 | bar: -529 C to 0.86553 J
56
57 | bar: -529 C to 0.86553 J
58
59 | bar: -529 C to 0.86553 J
60
61 | bar: -529 C to 0.86553 J
62
63 | bar: -529 C to 0.86553 J
64
65 | bar: -529 C to 0.86553 J
66
67 | bar: -529 C to 0.86553 J
68
69 | bar: -529 C to 0.86553 J
70
71 | bar: -529 C to 0.86553 J
72
73 | bar: -529 C to 0.86553 J
74
75 | bar: -529 C to 0.86553 J
76
77 | bar: -529 C to 0.86553 J
78
79 | bar: -529 C to 0.86553 J
80
81 | bar: -529 C to 0.86553 J
82
83 | bar: -529 C to 0.86553 J
84
85 | bar: -529 C to 0.86553 J
86
87 | bar: -529 C to 0.86553 J
88
89 | bar: -529 C to 0.86553 J
90
91 | bar: -529 C to 0.86553 J
92
93 | bar: -529 C to 0.86553 J
94
95 | bar: -529 C to 0.86553 J
96
97 | bar: -529 C to 0.86553 J
98
99 | bar: -529 C to 0.86553 J
100
101020
Formulas:
STATUS = IF([E]=0,"",([D]))
Note on C19: Insert title or code of the performing organization who will accomplish the task.
Note on G19: Insert date that task should be finished.
Note on H19: IF task requires labor hours, insert hours to do the task. IF task requires non-labor costs, insert a zero (0) in this cell.
Note on I19: IF task requires labor, insert labor hourly rate; IF task is non-labor insert dollar amount.

## Trends
Title and Year | Analysis & Action Plan
|  | Date | Measure | Target | Alpha | Bravo | Hi=1 Low=0 | Scores
Responsibility | Responsibility (for analysis and action plan): | Jan |  |  |  |  | 1
Workforce Focus Team | Name | Feb |  |  |  |  | 1
|  | Mar |  |  |  |  | 1
Results Group | Responsibility (for collection and validity): | Apr |  |  |  |  | 1
7.3 Workforce Focused Results | Name | May |  |  |  |  | 1
| Benchmarks (competitor or comparitive organizations) | Jun |  |  |  |  | 1
Measure Title | Alpha Organization | Jul |  |  |  |  | 1
Title and Year | Bravo Organization | Aug |  |  |  |  | 1
|  | Sep |  |  |  |  | 1
Source: - Frequency: - Format: | Date Refreshed | Oct |  |  |  |  | 1
Data Log | 11/30/2020 | Nov |  |  |  |  | 1
|  | Dec |  |  |  |  | 1
Guidelines for Data Entry
Note on E2: Input Trends Analysis narrative and Action Plan: Explain what happened, and how Results will be improved (who, what, when)
Note on H2: PERFORMANCE REVIEW GUIDELINES 1. The TARGET is approved by senior leaders and LFT 2. Then MEASURE should be trending toward Target 3. IF Measure is trending away from Target then the Analysis and Action Plan are manditory 4. IF Measure has arrived at the Target or has past the Target value then the Target value should be changed to set a new goal. 5. If Benchmarks (Alpha and Bravo lines) are available from competitor, comparative organizations or other benchmark sources then the title of the benchmark should replace Alpha and Bravo titles. 6. Alpha and Bravo lines can also be replaced by Upper and Lower Limits in reference to the Measure. These values might be from calculations such as those used in statistical process control. (End)
Note on N5: Input 1 if Target should be higher than Measure Input 0 if Target should be lower than Measure
Note on C18: INSTRUCTIONS FOR INPUT OF DATA INTO M1-M20 TABS 1. Use the Metrics List or other sources to select a particular measure that creates or drives RESULTS 2. Select Tab (M1 to M20) 3. Input the Chart Information (below chart) > Responsibility (name of Focus Team) > Measure and Year (e.g., Workforce Satisfaction 2020) > Metric or Measure Source (e.g., Data Log or other source) > Responsibility Name (for analysis and action plan) > Responsibility Name (for collection and validity of data) > Benchmarks (2) Rename Alpha and Bravo Organizations) > How weekly data are calculated (input sum or average) - The formulas in all data cells calculate sum or average 4. The person responsible for collection and validity of data determines the source and type of data to be collected, as well as the frequency. A separate log or spreadsheet may be needed to collect weekly totals. Examples are shown in the Metrics List tab. 5. Collect the DATA - The data are collected each week or eacg month as the data become available. Examples: > Units delivered, defects, new orders, etc. may have more than one count per week >Survey results may occur monthly, semi-annually or yearly 6. Input the DATA LOG Values (Data Log is below DATA CHART) > Input the counts or values in weeks they occur > The OE21 Datalog sums or averages all weekly values input and rolls them into the end of month total (a formula) > The end of month totals for all 12 months roll up to the DATA TABLE above the DATA LOG. 7. Go to the Chart and view the results. The person responsible for Analysis and Action Plan observes the results of data input on the graphical Chart. > The MEASURE is colored blue. The Measure is used to provide a linear forcast of the measures future value (dotted blue line) > The TARGET is colored black. The Target is used to set a goal (value) that the Measure should arrive at. The Target should be approved or set by the Leadership Focus Team for all measures. > The BENCHMARKS are colored Green or Red. If benchmarks are available, the names Alpha and Bravo should be replaced by the names of the competitor or comparative organization. >The values of the Alpha and Bravo benchmarks may not be available due to competitor protections. If available, they may be used as ideal comparisons of their performance against this organization's performance. 8. ANALYSIS AND ACTION PLAN - The person responsible for Analysis and Action Plan uses the results of data and graphical Chart, along with internal information to input the narrative Analysis and Action Plan. This narrative is manditory in cases where the Measure is trending away from the Target. The narrative is recommended even if the Measure is trending toward or has arrived at the Target value. 9. RAISING THE BAR - In cases where the Measure has intersected the Target, it is usually appropriate to raise the value of the Target higher to encourge continuous improvement. (End)
(Example Analysis)
Workforce satisfaction is gradually trending toward target values and should reach target by mid-year (linear measures should hit target by Oct 1, 2020).
The recent favorable trend appears to be due to new benefits for child care provided. The HR Director will continue to interview workers to learn more about what they like and do not like.
(Example Action Plan)
A revised Workforce Satisfaction Plan will be provided to the Leadership Focus Team by the HR Manager on or before 15-May-2020."